## Backlog
ID | Epic | Item / Title | Type | User Story | Acceptance Criteria | Priority | Phase | Estimate | Status | Maps To
E0-1 | E0 Foundations | User roles & extended profile | Story | As a user, I want the app to know whether I'm an adopter, owner, or vet, so it shows me the right features. | users doc has role field (adopter¦vet¦admin) + phone/city/bio; role defaults to adopter on sign-up. | Must | 1 | M | Done | Cross-cutting
E0-2 | E0 Foundations | Firestore data model & security rules | Story | As the team, we want a documented schema and locked-down rules so data is consistent and safe. | Collections for animals, products, orders, vets, appointments, chats, favorites; rules deployed; indexes created. | Must | 1 | M | Done | Backend
E0-3 | E0 Foundations | Reusable UI & error/loading states | Story | As a developer, I want shared widgets so screens look consistent and handle empty/error/loading. | Shared AppScaffold, list skeletons, empty-state and error-retry widgets; extended theme colors. | Must | 1 | S | Done | Cross-cutting
E0-4 | E0 Foundations | Image upload service | Story | As a user, I want to attach photos (animals, chat) stored in Firebase Storage. | StorageService wraps image_picker + firebase_storage, returns URL; compression, progress, failure handled. | Must | 1 | S | Blocked | Cross-cutting
E0-5 | E0 Foundations | Fix hardcoded Home greeting | Story | As a logged-in user, I want Home to greet me by my real name, not the hardcoded 'Hiba'. | Home reads current user's name from Firestore via a use case. | Must | 1 | S | Done | Home
E1-1 | E1 Adoption | Browse adoptable animals | Story | As an adopter, I want to browse a feed of animals available for adoption so I can find one. | Grid/list of animal cards; pull-to-refresh; pagination; empty state; status==available. | Must | 1 | M | Done | Home/Adopt
E1-2 | E1 Adoption | Filter & search animals | Story | As an adopter, I want to filter by species, breed, age, size and city so I see relevant matches. | Filter chips + search field; results update live; no-results state; Firestore indexes. | Should | 4 | M | Done | Home/Adopt
E1-3 | E1 Adoption | Animal detail screen | Story | As an adopter, I want a detailed page with photos and full info so I can decide. | Image carousel, description, health/vaccination notes, owner info, Request-adoption CTA, favorite toggle. | Must | 1 | S | Done | Home/Adopt
E1-4 | E1 Adoption | Request to adopt | Story | As an adopter, I want to send an adoption request to the animal's owner so we can proceed. | Creates adoption_requests doc (pending); owner notified; duplicate requests prevented. | Must | 1 | M | Done | Home/Adopt
E1-5 | E1 Adoption | List my animal for adoption | Story | As a pet owner, I want to post an animal I can no longer keep so others can adopt it. | Multi-step form (photos, species, breed, age, gender, description, location) -> animals status=available. | Must | 1 | M | Done | Home/Adopt
E1-6 | E1 Adoption | Manage my listings & requests | Story | As a pet owner, I want to see my posted animals and incoming requests so I can accept/decline. | My Listings + request counts; accept sets adopted & notifies; decline updates; edit/delete listing. | Must | 1 | M | Done | Home/Adopt
E1-7 | E1 Adoption | Favorites / saved animals | Story | As an adopter, I want to save animals I like so I can revisit them. | Heart toggle persists to users/{uid}/favorites; Saved screen lists them. | Should | 4 | S | Done | Home/Adopt
E2-1 | E2 Shop | Product catalog | Story | As a shopper, I want to browse products (food, toys, accessories, health) by category. | Category tabs/grid; product cards (image, name, price, rating); search; pagination. | Should | 2 | M | Done | Cart
E2-2 | E2 Shop | Product detail | Story | As a shopper, I want full product info so I can decide to buy. | Images, description, price, stock, quantity selector, Add-to-cart. | Should | 2 | S | Done | Cart
E2-3 | E2 Shop | Cart | Story | As a shopper, I want a cart so I can collect items and adjust quantities before checkout. | Add/remove/update qty; live subtotal; persists per user; badge on Cart tab. | Should | 2 | M | Done | Cart
E2-4 | E2 Shop | Checkout & orders | Story | As a shopper, I want to place an order with a delivery address so my supplies arrive. | Address form; order summary; place-order -> orders (pending); cart clears; confirmation screen. | Should | 2 | M | Done | Cart
E2-5 | E2 Shop | Order history & tracking | Story | As a shopper, I want to see my past and current orders with status so I can track them. | My Orders list with status (pending->shipped->delivered); order detail. | Should | 2 | S | Done | Cart
E2-6 | E2 Shop | Payment integration | Spike | As a shopper, I want to pay online for my supplies. | Depends on payments spike (E4-3); MVP ships cash-on-delivery only. | Could | 4 | M | Blocked | Cart
E3-1 | E3 Vet | Vet directory | Story | As a pet owner, I want to browse available vets with specialties and ratings so I can pick one. | List of vets (photo, name, specialty, clinic, city, rating); search/filter by specialty & city. | Should | 3 | M | Done | Chat
E3-2 | E3 Vet | Vet profile | Story | As a pet owner, I want a vet's detail page so I can choose an action (chat/call/book). | Bio, specialties, clinic address, hours, three CTAs (Chat, Call, Book appointment). | Should | 3 | S | Done | Chat
E3-3 | E3 Vet | 1:1 chat with vet | Story | As a pet owner, I want to text a vet so I can ask about my animal. | Real-time messages via chats/{id}/messages; text + image; read receipts; uses bubble; chat list. | Should | 3 | L | Done | Chat
E3-4 | E3 Vet | Voice / video call with vet | Spike | As a pet owner, I want to call a vet so I can talk directly. | Phase 1: launch device dialer (tel:) via url_launcher. Phase 2: in-app calling (spike E4-4). | Could | 4 | M | Blocked | Chat
E3-5 | E3 Vet | Book an appointment | Story | As a pet owner, I want to book an appointment slot with a vet so I get dedicated time. | Vet availability; pick date/time; appointments doc (requested); double-booking prevented; both notified. | Should | 3 | L | Done | Chat
E3-6 | E3 Vet | Manage appointments | Story | As a pet owner or vet, I want to see, confirm, reschedule or cancel appointments. | My Appointments list; vet dashboard to confirm/decline/complete; status transitions; cancel frees slot. | Should | 3 | M | Done | Chat
E4-1 | E4 Cross-cutting | Push notifications | Story | As a user, I want to be notified of requests, orders, messages and appointment reminders. | FCM; token storage; Cloud Function triggers for each event. | Should | 3 | M | Blocked | Cross-cutting
E4-2 | E4 Cross-cutting | Global search & discovery | Story | As a user, I want unified search across animals, products and vets. | Single search surface returning mixed results. | Could | 4 | M | Done | Cross-cutting
E4-3 | E4 Cross-cutting | Payments spike + integration | Spike | As the team, we need a payment approach for shop and paid appointments. | Evaluate Stripe vs local gateways; deliver decision doc + integration story; MVP = cash-on-delivery. | Should | 4 | M | Done | Cross-cutting
E4-4 | E4 Cross-cutting | In-app calling spike | Spike | As the team, we need a calling approach for vet calls (Phase 2). | Evaluate Agora / Twilio / WebRTC; deliver decision doc. | Could | 4 | S | Done | Cross-cutting
E4-5 | E4 Cross-cutting | Admin / moderation | Story | As an admin, I want to moderate content and approve vets so the marketplace stays safe. | Report listings; approve vets; remove content. | Could | 4 | M | Done | Cross-cutting
E4-6 | E4 Cross-cutting | Analytics & crash reporting | Story | As the team, we want usage analytics and crash reports. | Firebase Analytics events + Crashlytics. | Could | 4 | S | In progress | Cross-cutting
E4-7 | E4 Cross-cutting | Automated tests | Story | As the team, we want tests so refactors are safe (test/ folder is currently empty). | Unit tests for use cases/cubits; widget tests for key screens. | Should | 4 | M | Done | Cross-cutting

## Summary
Adopt Animal — Backlog Summary
Total items
By Priority |  | By Phase
Priority | Count | Phase | Count
Must |  | 1 - MVP adoption
Should |  | 2 - Shop
Could |  | 3 - Vet care
4 - Polish/scale
By Epic |  | By Status (live)
Epic | Count | Status | Count
E0 Foundations |  | Not started
E1 Adoption |  | In progress
E2 Shop |  | Blocked
E3 Vet |  | Done
E4 Cross-cutting
% Done

## Legend
How to use this backlog
Column | Meaning
ID | Epic-story code (E<epic>-<n>). Matches BACKLOG.md.
Epic | E0 Foundations, E1 Adoption, E2 Shop, E3 Vet, E4 Cross-cutting.
Type | Story = buildable feature; Spike = research/decision task.
Priority | Must / Should / Could (MoSCoW). Editable dropdown; Must=orange, Should=yellow, Could=grey.
Phase | Suggested rollout: 1 MVP adoption, 2 Shop, 3 Vet care, 4 Polish/scale. Editable dropdown.
Estimate | Rough size: S (<1 day), M (1-3 days), L (3+ days). Editable dropdown.
Status | Not started / In progress / Blocked / Done. Editable dropdown; drives the Summary counts.
Maps To | Where it lives in the app (Home/Adopt, Cart, Chat, Cross-cutting, Backend).
Tip | Use the filter arrows on the Backlog header row to slice by Epic, Priority, Phase or Status.
Tip | Update the Status column and the Summary tab recalculates automatically.
Note | Estimates are rough placeholders — re-point with your team before committing to a sprint.